## Slide 1: Financial overview of the project implementation
Modernization and Harmonization of Tourism Study Programs in Serbia 544543-TEMPUS-1-2013-1-RS-TEMPUS-JPCR

## Slide 2: Statement of the Costs Incurred
 |  | 1. PROJECT COSTS € Estimated budget of the project (Annex II) |  | 2. PROJECT EXPENDITURE TO DATE € |  |  | 
 |  |  |  | Declared payed from Tempus | Declared Co-financed |  | TOTAL declared
I | Staff Costs | 257 ć97,50 € |  | 1ć8 094,91 € | 17 304,39 € |  | 185 399,30 €
II | Travel Costs & Costs of Stay | 137 935,00 € |  | 134 371,35 € | 4 ć15,85 € |  | 138 987,20 €
III | Equipment | 179 ć40,00 € |  | 12ć 729,49 € | 17 473,41 € |  | 144 202,90 €
IV | Printing & Publishing | 25 500,00 € |  | 14 555,77 € | 1 214,ć8 € |  | 15 770,45 €
V | Other Costs | ć0 520,00 € |  | 14 724,40 € | 13 125,49 € |  | 27 849,89 €
VI | Indirect Costs | 4ć 290,47 € |  | 5 221,895 € |  | 5 221,895 € | 
 |  |  |  | Total | Total | TOTAL | 
TOTAL ELIGIBLE COSTS |  | 707 582,97 € |  | 4ć3 ć97,815 € | 53 733,82 € | 517 431,ć35 € | 

## Slide 3: Total Project finance
 |  | 3. PROJECT FINANCE €
Co-financing |  | 70 7ć1,00 €
Total from the Tempus grant |  | ć3ć 821,97 €
TOTAL PROJECT FINANCE |  | 707 582,97 €

## Slide 4: Co-financing requirements
Partner | Acronym | Co-financing requirements
Business and Technical College of Applied Sciences | BTC | 25 781,379 €
High Business School of Leskovac | HBSL | 12 400,00 €
University of Kragujevac | UNIKG | 12 800,00 €
Tourism Organization of Western Serbia Region | TOWS | 2 193,559 €
Regional Chamber of Commerce, Uzice | RPK | 2 193,4755 €
Chamber of Commerce of Vojvodina | PKV | 2 193,4755 €
Tourism Organization of Leskovac | TOL | 2 145,25ć €
University of Greenwich, London | UoG | 4 800,415 €
Technological Educational Institute of Piraeus, Athens | TEIP | 3 73ć,70 €
University of Agricultural Sciences and Veterinary Medicine, Cluj-Napoca | USAMV | 2 51ć,74 €

## Slide 5
Finansijski menadžment
TEMPUS projekata

## Slide 6
 | Staff Costs
Generalno:
Maksimalno 40 % direktnih troškova.
Zaposleni u javnoj administraciji (npr. ministarstva) ne mogu biti
plaćeni sa projekta.
Salary rates ne mogu biti veće od propisanih maksimuma i moraju
da odgovaraju institucionalnoj politici redovnih zarada.
Salary rates se računaju na osnovu tipova poslova na projektu, a ne
na osnovu statusa zaposlenog.
Veća salary rate od propisane može se primenitu samo ako
konkretna osoba za isti posao na instituciji prima veću zaradu
(preporučuje se traženje prethodne dozvole EACEA).

## Slide 7
 | Staff Costs
Za pravdanje pred EACEA potrebno je:
– U slučaju isplate honorara:
Convention for Staff
Time-sheet
Institucionalna politika
– Isplata kroz zaradu:
Convention for Staff
Time-sheet
Institucionalna politika
– Za veću salary rate
+ Platni listić (payslip)

## Slide 8
 | Staff Costs
Institucionalna politika
način 1 (2012, 2013)
– Na osnovu interne
odluke ustanove o
iznosima salary rates-a
za pojedine poslove.
– Kofinansiranje?
Institucionalna politika
način 2:
– Na osnovu redovne
zarade zaposlenog na toj
instituciji; Dokaz platni
listići

## Slide 9
 | Staff Costs
Za pravdanje u reviziji potrebno je:
– U slučaju isplate honorara:
Convention for Staff
Time Sheet
Ugovor
Rekapitulacija
OPJ obrazac (ili ekvivalentna e-potvrda)
Izvod iz banke za neto honorar, ali i za poreze i doprinose
– Isplata kroz zaradu:
Convention for Staff; odluka ustanove koja važi za sve
Time Sheet
Platni listić
OPJ (ili PPP) obrazac (ili ekvivalentna e-potvrda)
Izvod iz banke za neto zarade (poreza i doprinosa)

## Slide 10
 | Staff Costs
Vezano za Staff costs revizor još proverava:
status zaposlenog i uslove njegovog zaposlenja-
proverava ugovor ili payslip-ove
proverava da li postoje autorizovani i potpisani time
sheet-ovi za zaposlene
proverava daily rate za zaposlene kako se ne bi
razlikovali od dozvoljenih po pravilima EACA (uzima se
sa sve porezima i doprinosima, tzv. Bruto II)

## Slide 11
Travel costs i costs of stay
Genralno za zaposlene:
– Samo zaposleni na partnerskim ustanovama mogu
učestvovati u mobilnosti.
– Zaposlenima u javnoj administraciji (npr. ministarstva) može
biti plaćeni putni troškovi i dnevnice.
– Za sve mobilnosti koje su van sedišta partnerskih institucija ili
spadaju u aktivnosti koje nisu navedene u guidlines-u mora se
tražiti prethodna dozvola EACEA.
– Transport mora biti najekonomičniji.
– U travel costs mogu se uključiti troškovi vize, obaveznog
osiguranja.
– Costs of stay ne sme da prelazi propisane iznose dnevnica.

## Slide 12
Travel costs i costs of stay
Genralno za studente:
– U mobilnosti mogu učestvovati studenti počevši od završene druge godine
osnovnih studija.
– Dužina mobilnosti mora biti najmanje 2 nedelje za studijske posete i
intezivne kurseve, odnosno najmanje mesec dana za praksu, a
maksimalno 3 meseca.
– Mobinost radi učešća studentskih predstavnika na
menadžerskim/koordinativnim sastancima ili u aktivnostima na kontroli
kvaliteta projekta može biti kraće od 2 nedelje i isplaćuju se dnevice kao
za zaposlene.
– Za sve mobilnosti koje su van sedišta partnerskih institucija ili ne spadaju
u nevedene aktivnosti mora se tražiti prethodna dozvola EACEA.
– Maksimalne dnevnice propisane za studente su drugačije nego za
zaposlene.

## Slide 13
Travel costs i costs of stay
Za pravdanje pred EACEA je potrebno:
IMR
Fakture za prevoz
Boarding pass-ovi, autobuske, vozne karte...
U slučaju putovana sopstvenim vozilom (ili vozilom
institucije) kopija internog dokumenta o načinu obračuna
putnih troškova po kilometru, koji ne sme prelaziti 0,22
evra po km.

## Slide 14
Travel costs i costs of stay
Za pravdanje u reviziji je potrebno:
– U slučaju putovanja u zemlji:
IMR
Putni nalog
Obračun putnog naloga
Fakture za smeštaj i prevoz i izvodi na kojima se vidi da su fakture
plaćene
Autobuske, vozne karte...
Izvodi iz banke ili blagajnički zapisi da su osobi isplaćeni putni
troškovi
OPJ obrasci (ili ekvivalentna e-potvrda) i izvodi iz banke da su
plaćeni porezi i doprinosi
Institucionalna politika, ako ikakva postoji

## Slide 15
Travel costs i costs of stay
Za pravdanje u reviziji je potrebno:
– U slučaju putovanja u inostranstvo:
IMR
Putni nalog (rešenja, odluke o upućivanju na službeni put)
Obračun putnih troškova
Fakture za smeštaj i prevoz i izvodi na kojima se vidi da su fakture
plaćene
Bordning passovi, autobuske karte, vozne karte...
Izvodi iz banke ili blagajnički zapisi o podizanju akontacije
Izvodi iz banke ili blagajnički zapisi da su osobi isplaćeni putni troškovi
ili o povraćaju dela akontacije
OPJ obrasci (ili ekvivalentna e-potvrda) i izvodi iz banke da su plaćeni
porezi i doprinosi

## Slide 16
Travel costs i costs of stay
Vezano za travel costs i costs of stay revizor proverava:
– da li postoje fakture od treće strane,
– da li postoje boarding passovi sa imenima i datumima,
autobuske, vozne karte sa datumima
– izvodi gde se vidi da su plaćene fakture i/ili da je novac
isplaćen osobi koja je putovala.
– Takodje proverava i da cost of stay ne prelazi daily rate
dozvoljen pravilima EACEA

## Slide 17
 | Equipment costs
Maksimalno 30 % direktnih troškova.
U opremu može spadati: (e-)knjige i časopisi, faks i fotokopir
mašine, račnari i periferije, softver, mašine i oprema za nastavu,
video projektori i prezenteri, televizori, instalacija interneta,
pristup on-line bazama knjiga i časopisa, održavanje, osiguranje,
transport i instalacioni troškovi opreme.
Porezi, carine i takse nisu prihvatljivi troškovi.
Za opremu preko 25.000 evra mora postojati dokumentacija o
postupku nabavke i najmanje tri ponude.
Institucija ne sme deliti nabavke na više manjih kako bi izbegla da
ima nabavku opreme preko 25.000 evra.
Za opremu preko 5.000 evra mora postojati sertifikat o poreklu
opreme (poreklo iz EU i partnerskih zemalja), za ostalu opremu
bilo kakva potvrda o poreklu. (2013)

## Slide 18
 | Equipment costs
Za pravdanje pred EACEA je potrebno:
– Faktura,
– Za opremu preko 25.000 evra dokumentacija o postupku
nabavke opreme i najmanje 3 ponude:
EACEA može tražiti prevođenje ove dokumentacije,
Faktura se šalje uz Finacial statement – Annex 4,
– Za opremu preko 5.000 evra po komadu sertifikat o poreklu.
(2013), a za opremu niže vrednosti bilo kakav dokument o
poreklu (2013)

## Slide 19
 | Equipment costs
Za pravdanje u reviziji je potrebno:
Celokupna dokumentacija o postupku nabavke opreme
Tri ponude za sve nabavke preko 25.000 evra I dokument o
evaluaciji ponuda
– Faktura,
– Otpremnica
– Prijemnica
– Inventarna lista
– Potvrda o oslobađanju od PDV-a
– Izvod iz banke da je faktura plaćena
– Sertifikat o poreklu opreme (potvrda o poreklu opreme)
2013

## Slide 20
 | Equipment costs
Vezano za equipment costs proverava:
– da li postoji dokumentacija o postupku nabavke preko 25000
evra i da li postoje tri ponude
– da li postoje ugovori, fakture, otpremnice i prijemnice i
odgovarajući izvodi
– ako postoji potvrda o oslobađanju od PDV-a
Ako se ne oslobađa od PDV-a institucija ga ne sme
zaračunati u troškove iskazane u finalnom izveštaju.
Ovo važi za sve kategorije direktnih troškova

## Slide 21
Printing and Publishing Costs
U PP može spadati: štampanje, objavljivanje (uključujući
elektronski format), fotokopiranje nastavnog materijala i ostale
dokumenatcije neophodne za projektne aktivnosti, web dizajn i
održavanje sajta (po fakturi)...

## Slide 22
 | Other Costs
U OC može spadati: disiminacija (reklamiranje u medijima,
promotivni materijal), iznajmljivanje prostora za disiminaciju (uz
autorizaciju), revizija, inter-project coaching (max. 2.500 evra),
bankarske provizije i podugovaranje za specifične aktivnosti.
Podugovaranje (2013) je moguće za: eksternu evaluaciju, kursevi
jezika, IT kursevi, prevodilačke usluge, web dizajn i održavanje
sajtova (po ugovoru)
Ako ukupno podugovaranje iznosi preko 10.000 evra mora se
tražiti prethodna dozvola EACEA. (2013, 2012)
Podugovaranja ne sme biti za nastavu i menadžment projekta.
Travel costs i costs of stay za podugovarače takođe spada u OC
(uz autorizaciju).

## Slide 23
PP & OC
Za pravdanje PP pred EACEA je potrebno:
– Faktura,
– Za PP preko 25.000 evra dokumentacija o nabavci i najmanje
3 ponude.
Za pravdanje OC pred EACEA je potrebno:
– Fakture ili Ugovori (podugovaranje) ili Izvodi (provizije)
– Za OC preko 25.000 evra dokumentacija o nabavci i najmanje
3 ponude.
– Za travel costs i costs of stay podugovarača sve kao i za travel
costs i costs of stay zaposlenih.
– Za staff costs eksperata kao i za staff costs zaposlenih.

## Slide 24
PP & OC
Za pravdanje u reviziji je potrebno:
– Faktura,
– Potvrda o oslobađanju od PDV-a
– Izvod iz banke da je faktura plaćena
– P&P primerci publikacija
U slučaju podugovaranja:
– Ugovori i/ili Fakture
– Potvrda o oslobađanju od PDV-a
– Izvodi iz banke da je plaćena faktura ili uplaćen
honorar

## Slide 25
 | Indirect Costs
Nije potrebna supporting dokumentacija.
Revizor i EACEA samo proveravaju da li IC ne prelaze 7%
vrednosti direktnih troškova iskazanih u finansijskom
izveštaju.
Indirektni troškovi mogu biti: institucionalne troškove,
fotokopiranje, kancelarijski materijal, poštanske usluge,
troškove telefona, upotrebu interneta (za razliku od
instalacije interneta – oprema)...
Kofinansiranje se ne može prikazati u okviru ove
kategorije troškova.

## Slide 26
Transferi između budžetskih linija
Svaka budžetska linija direktnih troškova može se
povećati na račun drugih budžetskih linija za
maksimalno 10 % vrednosti linije koja se uvećava bez
traženja prethodne dozvole EACEA.
Moguće je uvećati i staff costs i equipment preko 40%,
odnosno 30%.
Indirektni troškovi ne mogu se uvećavati.

## Slide 27
 | Revizorski izveštaj
Revizori dostavljaju izveštaj, u propisanom obliku koji
sadrži listu izuzetaka (ako postoje)
Revizori potpisuju sve fakture na iznose veće od 25.000
evra.
Takođe, revizori moraju da potpišu sve konvencije
osoba kojima je u zbiru za vreme trajanja projekta
isplaćeno više od 25.000 evra.
Revizorski izveštaj šalje se zajedno sa Finalnim
izveštajem projekta u Brisel.

## Slide 28
Outline
> Budget headings & ceilings
> Tendering procedures
> Subcontracting
> Exchange rates
> Financial Report & supporting documents
> External audit requirement
> Modifications to the budget
> Co-financing concept
> Determination of the final grant
> Payment cycle
> Ex-post audits
N.B. : Please note that this document has no legal value.
http://eacea.ec.europa.eu/tempus

## Slide 29
ANNEX II of the Grant Agreement
Estimated budget of the action
PROJECT COSTS | €
I Staff costs (max 40% of total eligible direct costs) | 400,000.00
II Travel costs, costs of stay | 300,000.00
III Equipment (max 30% of total eligible direct costs) | 200,000.00
IV Printing and publishing | 80,000.00
V Other costs | 20,000.00
Eligible direct costs (total I - V) | 1,000,000.00
VI Indirect costs (7% of total eligible direct costs) | 70,000.00
Total eligible costs (total I - VI) | 1,070,000.00
PROJECT FINANCE | €
Co-financing of at least 10% of the total eligible costs | 107,000.00
Tempus grant: includes financing to a maximum of 90% of the total | 963,000.00
eligible costs | 
TOTAL PROJECT FINANCE | 1,070,000.00
http://eacea.ec.europa.eu/tempus

## Slide 30
Budget headings & contractual ceilings
Staff costs (incl. replacement costs)
Max 40% of the total eligible direct costsCo-financing is subject to the 40% limit Up to 10% flexibility without authorisation Local salary rates to be applied
Travel costs and Costs of stay
Up to 10% flexibility without authorisation Travel costs: Actual costs per person
Costs of stay: daily allowances
Equipment
Max. 30% of the total eligible direct costsCo-financing is subject to the 30% limit Up to 10% flexibility without authorisation
Printing & Publishing
Up to 10% flexibility without authorisation
Other costs
Indirect costs
7% of the total eligible direct costs recalculated at the end of the project based on the actual eligible costs. Co-financing not permitted
http://eacea.ec.europa.eu/tempus

## Slide 31
I. Staff costs (incl. replacement costs)
Purpose
To cover the costs of staff directly necessary for the achievement of the results and not covered by other sources:
Administrative or academic tasks (3.1 Guidelines):
Course development, maintenance of online courses/website, etc.
Language / IT courses, translation services, evaluation activities when performed by internal staff (if sub-contracted 4 Other costs)
Replacement costs for EU staff (3.3 of Guidelines)
Contractual
rules
Staff costs should respect local salary rates and reflect the employing institution's usual policy on remuneration. Maximum reference daily rates: Guidelines/Annex 3.
Total expenditure for Staff Costs cannot exceed the 40% ceiling (with 10 % flexibility). Co-financing is also subject to the 40% ceiling.
Supporting
documents
The beneficiary shall retain:
For staff members: Staff Convention (Guidelines/Annex 1)
For external staff: Subcontract and invoice (plus 3 quotations if the contract is > EUR 25,000)
For replacement of EU teaching staff: confirmation of engagement from EU institution and Staff Convention The beneficiary shall provide:
Copies of subcontracts and invoices if the contract or remuneration is higher than EUR 25,000
Explanation & supporting documents to be given in the financial statement (final report) if higher salary rates are applied (Guidelines/Annex 3).
http://eacea.ec.europa.eu/tempus

## Slide 32
Example: Staff Costs – maximum eligible daily rates for EU staff (in €)
(gross rates)
Guidelines for the use of the Grant (Annex 3)
Country | Manager | Teacher | Technical | Administrative
Belgique/Belgie - BE 37ć 321 2ć0 203 |  |  |  | 
Bulgaria- BG 79 71 55 37 |  |  |  | 
Ceska Republika - CZ 144 144 104 75 |  |  |  | 
Danmark - DK 489 419 341 2ć7 |  |  |  | 
Deutschland - DE 3ć3 315 253 195 |  |  |  | 
Eesti - EE 117 107 75 53 |  |  |  | 
Ellas – EL 2ć7 228 187 145 |  |  |  | 
Espana –ES 295 2ć5 204 143 |  |  |  | 
France - FR 424 359 235 179 |  |  |  | 
Ireland – IE 479 417 348 255 |  |  |  | 
Italia - IT | 5ć8 | 332 | 225 | 187
http://eacea.ec.europa.eu/tempus

## Slide 33
 | II. Travel costs and costs of stay - Staff | 
Purpose
To cover the costs of travel and subsistence allowances of staff and subcontractors for motilities linked to: teaching/training assignments, retraining, update of courses, practical placements, short visits for coordination and planning, language training, dissemination visits.
Contractual
rules
The budget for Travel Costs and Costs of Stay should:
cover only actual travel costs (including visa fee and related obligatory insurance, travel insurance and cancellation costs if justified)
cover the daily allowance: the ceilings per person indicated at point 4.4.3 of the Guidelines must be respected
Travel for research activities is not allowed
Supporting
documents
The beneficiary shall retain with the project accounts:
a SIGNED & filled-in Individual Mobility Report for each mobility using the standard form (Guidelines, Annex 2)
readable copies of travel tickets, invoices, boarding passes, receipts.
The beneficiary is not requested to send any supporting documents
with the Final report.
http://eacea.ec.europa.eu/tempus

## Slide 34
II. Staff = activities and mobility directions
Point 4.4.1 Guidelines
* General principle: mobilities between the participating project
Beneficiaries
Activity Direction
Assignments for teachers/trainers | 
 | *
 | PC 4 EU and PC / EU 4 PC
Re-training and up-dating courses | 
 | * PC 4 EU and PC
Practical placements | 
 | PC 4 EU and PC
Short visits for coordination and management meetings | 
 | ALL (PC and EU)
Language training | Within the PC itself or outside if
 | combined with another PC 4 EU and
 | PC mobility
Visit for dissemination purposes | Mobility is allowed to other institutions
 | in the participating Partner Countries
Specific EACEA authorisation is needed for any destination different from the above ones.
http://eacea.ec.europa.eu/tempus

## Slide 35
II. Travel costs and costs of stay - Students | 
Contractual
rules
Supporting
documents
Purpose
To cover the costs of travel and subsistence allowances of students for mobilities linked to: study periods abroad, practical placements in an enterprise, intensive courses for Partner Country students, participation of student representatives in management coordination meetings & QC.
The budget for Travel Costs and Costs of Stay should :
cover only actual travel costs (including visa fee and related obligatory insurance, travel insurance and cancellation costs if justified)
cover a monthly allowance for subsistence / accommodation / local transport and personal insurance: the ceiling per month and per person indicated at point 4.5.3 of the Guidelines must be respected.
Host universities can claim institutional costs for receiving students for study period from abroad (point 4.5.4 of Guidelines)
The duration of student mobilities should be minimum 2 weeks and
maximum 3 months.
The beneficiary shall retain:
a SIGNED & filled-in Individual Mobility Report for each mobility using the standard form (Guidelines/Annex 2)
readable copies of travel tickets, invoices, boarding passes, receipts.
The beneficiary is not requested to send any supporting documents
with the Final report.
http://eacea.ec.europa.eu/tempus

## Slide 36
II. Students - activities / mobility directions
Point 4.5.1 Guidelines
General principle: mobilities between the consortium members
Activity Direction Duration
 | EU 4 PC | Min 2 weeks Max 3 months
Study period |  | 
 | PC 4 PC and EU | 
 | EU 4 PC | Min 1 month Max 3 months
Practical placement |  | 
 | PC 4 EU and PC | 
 |  | Min 2 weeks Max 3 months
Intensive course | PC 4 EU and PC | 
Student representatives | PC and EU | shorter durations accepted, rates @ teacher level
from PC and EU in |  | 
coordination & QC meet. |  | 
 | 4 PC and EU | 
Specific EACEA authorisation is requested for any destination/duration
different from the above ones.
http://eacea.ec.europa.eu/tempus

## Slide 37
III. Equipment
Purpose
To cover the costs of equipment directly relevant to the project’s Objectives (hardware an software), the costs for installing internet connection, for access to databases, for equipment insurance/transport/installation, for maintenance of equipment.
Prior authorisation required for hire of equipment.
Contractual
rules
The equipment must:
be exclusively for PC universities included in the partnership (JP)
be exclusively for PC universities/institutions/organisations included in the partnership (SM) Not public administration!
be exempt from VAT and custom duties (they are not eligible)
Depreciation does not apply: the overall cost of equipment is covered. Total expenses for equipment cannot exceed the 30% ceiling (10% flexibility). Co-financing is also subject to the 30% ceiling.
Supporting
documents
The beneficiary shall retain readable copies of:
all invoices for all equipment declared costs
proofs of tendering procedure (min. 3 quotations) for purchases above EUR 25,000 (no ‘saucissonage’!).
The Beneficiary shall provide:
Readable copies of invoices if the purchase is above EUR 25,000.
The names of the firms consulted (min. 3) have to be indicated in the Financial statement (Final report).
http://eacea.ec.europa.eu/tempus

## Slide 38
IV. Printing & Publishing
Printing & Publishing budget heading can cover:
Purpose
paper and electronic productions (electronic form)
design, development and establishment of website
photocopying of teaching materials/documentation
General photocopying 4 Indirect Costs
Contractual
rules
Internal staff costs may not be covered by this budget heading
(i.e. web updating and web maintenance).
Supporting
documents
The beneficiary shall retain with the project accounts readable copies of all invoices (internal invoices to be issued for in-house printing and publishing).
The beneficiary is not requested to send any supporting document
with the Final report.
http://eacea.ec.europa.eu/tempus

## Slide 39
V. Other costs
Other costs budget heading can cover:
Costs related to dissemination of information (advertising in media, promotional materials such as pen, bags, posters, etc.)
Inter-project coaching (maximum of EUR 2,500)
Bank charges (including bank guarantee charges where requested)
External audit fees
Language / IT courses, translation services, evaluation activities if subcontracted to external service providers (when performed by internal
Purpose
staff 4 Staff Costs)
Hire of premises for dissemination events (prior EACEA authorisation needed).
Ineligible costs: hospitality costs, costs related to the use of materials & equipment incurred by institutions when hosting students/ staff, registration fees for courses/conferences, exchange losses, etc.
Contractual
rules
The beneficiary shall retain with the project's accounts readable
Supporting
documents
copies of all invoices and bank statements.
The beneficiary is not requested to send any supporting document
with the Final report.
http://eacea.ec.europa.eu/tempus

## Slide 40
VI. Indirect Costs
Purpose
Indirect Costs should be eligible and can cover:
stationary, office supplies, general photocopying
postage and telecommunication costs related to the project
use of internet/communication software
Eligible for flat-rate funding of 7% of the total eligible direct costs (Art.
I.4.2 and II.14.3).
Contractual
rules
At the end of the project, the Indirect Costs incurred and declared will be considered eligible as long as they:
do not exceed the absolute amount shown for Indirect Costs in Annex II of the Grant Agreement (approved budget)
do not represent more than 7% of the total actual eligible direct costs following the financial assessment.
Supporting
documents
NO supporting document is required.
NO co-financing is permitted under this budget heading
http://eacea.ec.europa.eu/tempus

## Slide 41
Tendering Procedure
The beneficiary shall apply the ‘award of contract’ procedure
(Art. II.9) when:
purchasing any kind of goods or services in the framework of the
Tempus project (under any budget heading, so not only ‘equipment’)
BUT ONLY IF
the amount of the purchase/sub-contract exceeds
the threshold of EUR 25,000
Proof of awarding procedure (at least 3 quotations) should be retained
with the project accounts
The names of the providers consulted (min. 3) shall be indicated in the final
financial statement of the Final Report.
N.B. The purchase cannot be split into smaller contracts with
individual amounts lower than the threshold.
http://eacea.ec.europa.eu/tempus

## Slide 42
SUB-CONTRACTING
ALWAYS PRIOR APPROVAL BY EACEA (even if mentioned in the
application! See FAQ n°51)
Should follow the procedures mentioned under Article 11.9;
tenders are required for amounts larger than € 25,000
To be allocated to the same budget headings as internal
expenses, except for:
External language & translation services (other costs)
External quality evaluations & audits (other costs)
External IT courses (other costs)
See also overview in FAQ n°28!
http://eacea.ec.europa.eu/tempus

## Slide 43
Exchange rates
All transactions ≠ EUR must be converted and reported in
EUR in the Financial Statement of the Final Report:
Which exchange rate?
from the start of the eligibility period until the date that the second pre-
financing is received: the rate of the month in which you received the
first pre-financing should be applied
from the date that the second pre-financing is received until the end of
the eligibility period: the rate of the month in which you received the
second pre-financing should be applied
The rate to be applied is the monthly accounting rate established
by the Commission and published on its website:
httcl://ec.eurocla.eu/budget/inforeuro
N.B. Exchange losses are not eligible.
http://eacea.ec.europa.eu/tempus

## Slide 44
Summary table: supporting documents
Budget heading | Supporting documents | 
 | To be submitted | To be kept with project accounts (upon request of EACEA, the beneficiary should be able to send the supporting docs. immediately)
I. Staff Costs | Copy of the sub- contract and invoice when a sub-contract is above € 25,000 Formal justification for higher salary rates | Staff Conventions for staff members Sub-contracts and invoices for external staff For a sub-contract above € 25 000, docs on the tendering procedure (min 3 quotations). For replacement costs, confirmation from the EU institution that the vacated role was filled for the period in question + Convention for each staff member filling the vacated role.
Travel Costs & Costs of Stay | None | Individual mobility reports and all copies of travel tickets, boarding passes, invoices, receipts.
Equipment | Copy of invoices for equipment with a total value above € 25,000* | All invoices Three estimates / quotations for equipment purchases above € 25,000.
* (The names of the companies contacted have to be indicated in the Final Report)
http://eacea.ec.europa.eu/tempus

## Slide 45
Summary table: supporting documents
Budget heading | Supporting documents | 
 | To be submitted | To be kept with project accounts (upon request of EACEA, the beneficiary should be able to send the supporting documents immediately)
Printing & Publishing | None | All invoices
Other Costs | None | All invoices, bank statements
Indirect Costs | None | None, but should be identifiable and justifiable (Art. II.4.3)
An Audit Report on the action's financial statements and underlying
accounts must be submitted for grants > € 750,000.
http://eacea.ec.europa.eu/tempus

## Slide 46
Financial Report & supporting documents
Detailed (descriptive) financial tables must be provided to justify
all expenses. Note that also gained bank interests MUST be
declared. Failing to do so is considered FRAUD!
The rules on supporting documents apply for both expenditure
paid by Tempus and co-financed!
General advice:
Contact EACEA in case of doubt
If necessary, please provide detailed explanations in the financial
statement
Collect the required supporting documents as soon as the expenditure is
incurred
http://eacea.ec.europa.eu/tempus

## Slide 47
EXTERNAL AUDIT REQUIREMENT
Obligatory for grants exceeding € 750,000
WHAT?
Verification whether costs are declared correctly and truthfully and backed by
proper supporting documents, in accordance with the provisions in the GA.
See the detailed overview in FAQ n° 3 on our website!
BY WHOM?
By a nationally certified auditor with the linguistic competences (the audit
report should be written in the project language!).
COST?
Don’t forget to foresee these costs under ‘Other Costs’!
They may amount between € 5,000 and € 12,000.
http://eacea.ec.europa.eu/tempus

## Slide 48
Modifications to the Budget
5 PRIOR written authorisation by EACEA is needed for any increase of the
approved amount allocated under each budget heading of direct costs of
more than 10%.
5 Requests must indicate the reason and the impact of such budget
modifications on the activities and the expected outcomes of the
modification. It must be submitted one month before the end of the
eligibility period at the latest.
5 The ceiling for equipment and staff costs (30% and 40% of the total
eligible direct costs shown in Annex II) is not subject to negotiation. The
flexibility of 10% applies also to these ceilings.
5 Indirect Costs are not subject to budget modification and the 10%
flexibility does not apply to Indirect Costs.
http://eacea.ec.europa.eu/tempus

## Slide 49
Co-financing concept
The Tempus grant contribution may not exceed 90% of the total
project budget (= Tempus + co-financing) considered eligible at the
end of the project;
The co-financing percentage is specific for each project (and indicated
in Art. I.4 of your Grant Agreement).
Actual Co-financing (minimum 10%):
+ should be declared and justified in the Final Report and will be
considered and assessed for the calculation of the total eligible costs at the
end of the project;
+ cannot cover costs which are not eligible for Tempus funding;
+ can be declared under any budget heading except “Indirect Costs”;
+ has to respect the same rules on supporting documents which apply for
the expenditure paid by Tempus.
http://eacea.ec.europa.eu/tempus

## Slide 50
Determination of the final grant
Art. II.17 Grant Agreement
The final grant will correspond to the lowest amount among the
following ceilings calculated at the end of the project:
Ceiling A: % of the actual total eligible costs at the end
of the project as indicated in art. I.4.3
Ceiling B: Total declared expenditure minus declared
co-financing amount
Ceiling C: Maximum Tempus Grant amount = amount
indicated in art. I.4.3
http://eacea.ec.europa.eu/tempus

## Slide 51
Assumption: all declared expenditure is eligible including indirect costs
Determination of the final grant
Art. I.4.2 The total budget (incl. co-financing): ex. € 1,070,000 Art. I.4.3 Maximum EU grant in amount: ex. EUR 9ć3,000 = 90% * of total eligible costs
PROJECT COSTS | Approved budget €
I Staff costs | 400,000.00
II Travel costs, costs of stay | 300,000.00
III Equipment | 200,000.00
IV Printing and publishing | 80,000.00
V Other costs | 20,000.00
Eligible direct costs (total I - V) | 1,000,000.00
VI Indirect costs (7% of total eligible direct costs) | 70,000.00
Total eligible costs (total I - VI) | 1,070,000.00
PROJECT FINANCE | €
Co-financing of at least 10% of the total eligible costs | 107,000.00
Tempus grant: includes financing to a maximum of 90% of the total direct costs | 9ć3,000.00
TOTAL PROJECT FINANCE | 1,070,000.00
DECLARED PAID BY TEMPUS | DECLARED CO-FINANCED | TOTAL DECLARED EXPENDITURE €
290,000.00 | 10,000.00 | 300,000.00
250,000.00 | 50,000.00 | 300,000.00
95,000.00 | 5,000.00 | 100,000.00
35,000.00 | 5,000.00 | 40,000.00
10,000.00 | 0.00 | 10,000.00
ć80.000,00 | 70.000,00 | 750.000,00
52,500.00* |  | 52,500.00*
732,500.00 | 70.000,00 | 802,500.00
Ceiling A: 90% of 802,500 = EUR 722,250 Ceiling B: 802,500- 70.000 = EUR 732,500 Ceiling C: EUR 9ć3,000
Final decision on payment:
* = 7% of the total eligible direct costs (co-financed + covered by Tempus) CEILING A = EUR 722,250
** = percentage varying according to each project (see Article I.4.3)
http://eacea.ec.europa.eu/tempus

## Slide 52
Assumption: all declared expenditure is eligible including indirect costs
Determination of the final grant
Art. I.4.2 The total budget (incl. co-financing): ex. € 1,070,000 Art. I.4.3 Maximum EU grant in amount: ex. EUR 9ć3,000 = 90% of total eligible costs
DECLARED PAID BY TEMPUS | DECLARED CO-FINANCED | TOTAL DECLARED EXPENDITURE €
320,000.00 | 80,000.00 | 400,000.00
230,000.00 | 20,000.00 | 250,000.00
80,000.00 | 20,000.00 | 100,000.00
30,000.00 | 10,000.00 | 40,000.00
10,000.00 | 0.00 | 10,000.00
ć70,000.00 | 130,000.00 | 800,000.00
5ć,000.00* |  | 5ć,000.00*
72ć,000.00 | 130.000,00 | 85ć,000.00
Ceiling A: 90% of 85ć,000 = EUR 770,400 Ceiling B: 85ć,000 - 130.000 = EUR 72ć,000 Ceiling C: EUR 9ć3.000
Final decision on payment:
PROJECT COSTS | Approved budget €
I Staff costs | 400,000.00
II Travel costs, costs of stay | 300,000.00
III Equipment | 200,000.00
IV Printing and publishing | 80,000.00
V Other costs | 20,000.00
Eligible direct costs (total I - V) | 1,000,000.00
VI Indirect costs (7% of total eligible direct costs) | 70,000.00
Total eligible costs (total I - VI) | 1,070,000.00
PROJECT FINANCE | €
Co-financing of at least 10% of the total eligible costs | 107,000.00
Tempus grant: includes financing to a maximum of 90% of the total eligible costs | 9ć3,000.00
TOTAL PROJECT FINANCE | 1,070,000.00
* = 7% of the total eligible direct costs (co-financed + covered by Tempus) ** = percentage varying according to each project (see Article I.4.3)
CEILING B = EUR 72ć,000
http://eacea.ec.europa.eu/tempus

## Slide 53
Assumption: all declared expenditure is eligible including indirect costs
Determination of the final grant
Art. I.4.2 The total budget (incl. co-financing): ex. € 1,070,000 Art. I.4.3 Maximum EU grant in amount: ex. EUR 9ć3,000 = 90% of total eligible costs
PROJECT COSTS | Approved budget €
I Staff costs | 400,000.00
II Travel costs, costs of stay | 300,000.00
III Equipment | 200,000.00
IV Printing and publishing | 80,000.00
V Other costs | 20,000.00
Eligible direct costs (total I - V) | 1,000,000.00
VI Indirect costs (7% of total eligible direct costs) | 70,000.00
Total eligible costs (total I - VI) | 1,070,000.00
PROJECT FINANCE | €
Co-financing of at least 10% of the total eligible costs | 107,000.00
Tempus grant: includes financing to a maximum of 90% of the total eligible costs | 9ć3,000.00
TOTAL PROJECT FINANCE | 1,070,000.00
DECLARED PAID BY TEMPUS | DECLARED CO-FINANCED | TOTAL DECLARED EXPENDITURE €
400,000.00 | 40,000.00 | 440,000.00
330,000.00 |  | 330,000.00
190,000.00 | 30,000.00 | 220,000.00
80,000.00 | 5,000.00 | 85,000.00
15,000.00 | 7,000.00 | 22,000.00
1,015,000.00 | 82,000.00 | 1,097,000.00
70,000.00* |  | 70,000.00*
1,085,000.00 | 82,000.00 | 1,1ć7,000.00
Ceiling A: 90% of 1,1ć7,000 = EUR 1,050,300 Ceiling B: 1,1ć7,000 -82,000 = EUR 1,085,000 Ceiling C: EUR 9ć3,000
Final decision on payment:
* = 7% of the total eligible direct costs (co-financed + covered by Tempus) CEILING C = EUR 9ć3,000
** = percentage varying according to each project (see Article I.4.3)
http://eacea.ec.europa.eu/tempus

## Slide 54
1st pre-financing: ć0%
45 days
Payment Cycle
- After the date when the last of the parties signs the GA .le (OR upon receipt of a financial guarantee if required)
2nd pre-financing: 30%
After the reception of :
Request for
Payment +
Intermediate
Report
0 Intermediate Report
(IR) in any case no later than half way through the project lifetime
balance: max 10%
- Following the approval of the Final Report including:
Financial
Statement &
Request for
Payment
Final
Report
(FR)
External
Audit
Report
a.ec.europa.eu/tempus

## Slide 55
AUDITS EX-POST
5 Can be proposed by EACEA or organised at random
S Up to 5 years after the project eligibility period has ended
S Verification whether:
the declared expenses have been actually incurred (for all ć
budget headings!);
the declared expenses are in accordance with the Grant
Agreement;
bank interests were gained and declared.
http://eacea.ec.europa.eu/tempus

## Slide 56
Reference documents
to be consulted
regularly:
Grant Agreement
Guidelines for the use of the grant
Frequently Asked Questions
http://eacea.ec.europa.eu/tempus
http://eacea.ec.europa.eu/tempus

## Slide 57
Pitanja?